## Bugs Overview
Bug Id | Summary | Environment | Browsers Platforms & Version | Priority | Severity | Steps to reproduce | Expected result | Actual result | Attachments | Reported by | Reported on | Status
1 | When the user clicks on "Академија за програмирање" button the page redirects the user to the "Академија за Front - End програмирање" | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | High | Critical | 1. navigate to https://bojan-dimeski.netlify.app/ 2.Click on"Академија за програмирање"button | The user should be redirected to a new page "Академија за Full - Stack програмирање"" | The user is redirected to "Академија за Front End" програмирање page | https://drive.google.com/file/d/1b56Ib1E2byKZ_GX99th8XiXGlvlpk7r0/view?usp=sharing | Goce Ristovski | 15.04.2022 | new
2 | When the user clicks on the Brainster logo on "Вработи наш студент"page, the page redirects to a broken link | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | High | Critical | 1. navigate to https://bojan-dimeski.netlify.app/ 2.Click on Врабори наш студент button 3.Click on"Brainster" logo | The user should be redirected to page index https://bojan-dimeski.netlify.app/ | The user is redirected to a broken link, " Page Not Found " is displayed | https://youfiles.herokuapp.com/videodictionary/?m=Video_Player_Drive&state=%7B%22ids%22:%5B%221u8HhfxdI-Lv7XXmgrbJ6EyzhzydXrvDF%22%5D,%22action%22:%22open%22,%22userId%22:%22106485357450584996308%22,%22resourceKeys%22:%7B%7D%7D | Goce Ristovski | 15.04.2022 | new
3 | Visuality of Index page is not appropriate | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | Medium | Cosmetic | 1. navigate to https://bojan-dimeski.netlify.app/ | The page should be as described | The banner differs from specifications, extra link for data science in navbar, wrong font… | https://youfiles.herokuapp.com/videodictionary/?m=Video_Player_Drive&state=%7B%22ids%22:%5B%221H5bMShm8v6tIpYS-VeNDi92k6zQW7FYL%22%5D,%22action%22:%22open%22,%22userId%22:%22106485357450584996308%22,%22resourceKeys%22:%7B%7D%7D | Goce Ristovski | 15.04.2022 | new
4 | Brainsters logo on index page is not funkcional | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | Medium | Major | 1. navigate to https://bojan-dimeski.netlify.app/ 2. Click on any of the 3 card filters 3.Click on"Brainster" logo | The user should be seen refreshed page without active filter | Filter is still on, page is not refreshed | https://youfiles.herokuapp.com/videodictionary/?m=Video_Player_Drive&state=%7B%22ids%22:%5B%2218Yst3UDKekyXKgTiTGilCOzy6OnpQPBB%22%5D,%22action%22:%22open%22,%22userId%22:%22106485357450584996308%22,%22resourceKeys%22:%7B%7D%7D | Goce Ristovski | 15.04.2022 | new
5 | Page Вработи наш студент is not properly designed | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | Medium | Cosmetic | 1. navigate to https://bojan-dimeski.netlify.app/ 2. Click on Вработи наш студент button | The page should be as described | It differs from description in button colours, font colours,navbar colours... | https://drive.google.com/file/d/1l3ctTNf9epJAHH-EsF0sUE2aCBOqzGnC/view?usp=sharing | Goce Ristovski | 15.04.2022 | new
6 | There should be 20 cards showed on index page | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 | Medium | Critical | 1. navigate to https://bojan-dimeski.netlify.app | There should be 20 cards in index page | There are 6 cards on the page and there is pagination, but overall number is 20 | https://drive.google.com/file/d/1leIifqv1pGfjQP77gJhdiPDzgDaZY5QN/view?usp=sharing | Goce Ristovski | 15.04.2022 | new
7 | The form Вработи наш студент is redirected to a new tab | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | Medium | Major | 1. navigate to https://bojan-dimeski.netlify.app/ 2.Click on Вработи наш студент button | The user should be redirected to a new page Вработи наш студент on the same tab | the user is redirected to desired page on a different tab | https://drive.google.com/file/d/1FMJgnDi3NI3zrn2PBlx4qiZvirN1vR5z/view?usp=sharing | Goce Ristovski | 15.04.2022 | new
8 | User can not enter student in system with valid data | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | Highest | Blocker | 1. navigate to https://bojan-dimeski.netlify.app/ 2.Click on Вработи наш студент button 3.Enter name in the Име и Презиме field - Vera Aceva 4.Enter company in Име на компанија field - Mlada Partizanka 5.Enter email in Контакт е-мајл field -bombebacala@google.com 6.Enter phone number in Контакт телефон field- 075 223 305 - 7.Chose any type of student from dropdownd menu 8. click on Испрати button | User should be able to enter student in the system by clicking Испрати button | No matter what we choose in Dropdown menu, it allways shows starting value Изберете тип на студент. | https://youfiles.herokuapp.com/videodictionary/?m=Video_Player_Drive&state=%7B%22ids%22:%5B%221TPxJBICO3IaWMtGbVXPadj4g3mL6_5CO%22%5D,%22action%22:%22open%22,%22userId%22:%22106485357450584996308%22,%22resourceKeys%22:%7B%7D%7D | Goce Ristovski | 15.04.2022 | new
9 | All Input fields should be mandatory | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | High | Critical | 1. navigate to https://bojan-dimeski.netlify.app/ 2. Click on Вработи наш студент button 3. All fields should be empty and drop down menu should not be clicked 5.Click on Испрати button | Bellow each input field and drop down meny should be appropriate error messsage that fields are mandatory | Under dropdown menu there is no message that needs to be choosen an option | https://drive.google.com/file/d/15_HjqrqBbFBgop3Bhilp9agt73GzOPVZ/view?usp=sharing | Goce Ristovski | 15.04.2022 | new
10 | Appropriate error message shoud be shown if wrong data is entered in any input field | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | Medium | Major | 1. navigate to https://bojan-dimeski.netlify.app/ 2.Click on Вработи наш студент button 3.Enter name in the Име и Презиме field - 123!@# 4.Enter company in Име на компанија field - 123!@# 5.Enter email in Контакт е-мајл field -mladapartizanka.com 6.Enter phone number in Контакт телефон field- qwe123 - 7.Chose any type of student from dropdownd menu 8. click on Испрати button | By entering invalid data on any input field, appropriate error message should be shown, and asking from user to enter valid data | Only Email field shows appropriate error message | https://drive.google.com/file/d/1Ey1kDryZIbylOG_zmbB2MzLAASKsuC2G/view?usp=sharing | Goce Ristovski | 15.04.2022 | new
11 | Entering wrong email form should not let user to continue and appropriate error message should be apear | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | High | Critical | 1. navigate to https://bojan-dimeski.netlify.app/ 2.Click on Вработи наш студент button 3.Enter valid data in all input fields exept dropdown menu and email 4.Enter invalid email in Контакт емајл field - google.com@bombebacala 5.Leave dropdown menu as it is 6. Click on Испрати button | The user should get message for invalid email and asked to enter a valid one | Error message is not shown and user is able to proced | https://youfiles.herokuapp.com/videodictionary/?m=Video_Player_Drive&state=%7B%22ids%22:%5B%221c62bYtNLJSEt7gcmKZLgWXm3M_zTuCXE%22%5D,%22action%22:%22open%22,%22userId%22:%22106485357450584996308%22,%22resourceKeys%22:%7B%7D%7D | Goce Ristovski | 15.04.2022 | new
12 | Error messages are not removed after filling them with data | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | Medium | Major | 1. Click on Вработи наш студент button found in the navigation bar of the page 2. Leave all fields empty 3. Click on Испрати button 4. Enter data in all input fields 5. Click Испрати button | Error messages that apear in emty fields should be removed by entering data in them | Error messages that apear in emty fields are not removed by entering data in them, insteaed user needs to refresh the page and then to klick on Испрати button to see if data is valid or not | https://drive.google.com/file/d/1fZBY2NoT_ufaiyC6j9xP4J_vmJGbRhQq/view?usp=sharing | Goce Ristovski | 15.04.2022 | new
13 | Card links are not funkcional | https://bojan-dimeski.netlify.app/ | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) Android 11 RKQ1.200826.002 - Xiaomi Redmi note 9 pro MIUI 12.5.5Stable - Firefox 99.2.0 | High | Critical | 1. Click on Дознај повеќе button on any card | User should be redirected to url: https://ahmetadm-project01.netlify.app/index.html# | User is navigate to the top of the page | https://drive.google.com/file/d/1a7U2xHBeyb4HOJW7zLc0cSRqzLa-YZXd/view?usp=sharing | Goce Ristovski | 15.04.2022 | new

## Improvements
Improvement ID | Summary | Browsers Platforms & Version | Steps | Expected result | Actual result (optional)
1 | Pagination on cards (bug id 6) | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) | 1. navigate to https://bojan-dimeski.netlify.app | Cards to have pagination instead of showing all 20 on the page | Here the bug is actualy improvement, it shows 6 cards with pagination on the botom, using that pagination we can see all 20 available cards
2 | Better order for cards in filter Проекти на студенти по академијата за Дизајн | Windows 10 Enterprise - Firefox 99.0.1 (64-bit) | 1. navigate to https://bojan-dimeski.netlify.app | Starting point of the shown cards to be from the left field, not from midle | Cards would be ordered from the first empty card field from left to right, not from any other